## Tasks and Timeline
Sauce & Spoon Project Plan
Task | Notes | Start Date | Due Date | Duration | Task Owner | Status | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
[7 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
Schedule Kick off Meeting
Milestone: Tablet research, purchase and delivery
Tablet implementation research
Generate quotes and review costs
Create contracts and statements of work for vendors
Tablet delivery
Milestone: Pilot test preparation
Schedule an electrician
Install tablets in the bar areas at the Downtown and North restaurant locations
Milestone: Tablet Menu Design
Connect the Sauce & Spoon marketing team with Terrific Tablets for branding
Source vendor for tablet menu interface
Tablet Menu Mockups and Designs creation
Approval for final menu design
Coding the application by vendor
Testing the menu in tablets
Milestone: Training Staff
Train management, FOH staff, and BOH staff
Conduct training in-house
Train the staff to update the menu
Conduct a test run before launch
Milestone: Pilot Launch
Create a launch day plan: staffing, troubleshooting, etc.
Milestone:Pilot Feedback
Implement a post-dining survey to assess customer satisfaction