## Tasks and Timeline
Sauce & Spoon Project Plan
Task | Notes | Start Date | Due Date | Duration | Task Owner | Status | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
[7 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
Schedule Kick off Meeting |  |  |  | 3 days
Milestone: Tablet research, purchase and delivery
Tablet implementation research |  |  |  | 3 days
Generate quotes and review costs |  |  |  | 1 day
Create contracts and statements of work for vendors |  |  |  | 1 day
Tablet delivery |  |  |  | 15 days
Milestone: Pilot test preparation
Schedule an electrician |  |  |  | 3 days
Install tablets in the bar areas at the Downtown and North restaurant locations |  |  |  | 3 days
Milestone: Tablet Menu Design
Connect the Sauce & Spoon marketing team with Terrific Tablets for branding |  |  |  | 3 days
Source vendor for tablet menu interface |  |  |  | 14 days
Tablet Menu Mockups and Designs creation |  |  |  | 5 days
Approval for final menu design |  |  |  | 10 days
Coding the application by vendor |  |  |  | 3 days
Testing the menu in tablets |  |  |  | 2 days
Milestone: Training Staff
Conduct training in-house |  |  |  | 15 days
Train the staff to update the menu |  |  |  | 1 day
Conduct a test run before launch |  |  |  | 1 day
Milestone: Pilot Launch
Create a launch day plan: staffing, troubleshooting, etc. |  |  |  | 5 days
Milestone:Pilot Feedback
Implement a post-dining survey to assess customer satisfaction |  |  |  | 10 days